|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task Name | | Duration (Days) | Start Days | Expected  End Date | Person assigned | Actual  End Date |
| **Inception** | Project plan | 1 | 20-june-2020 | 21-june-2020 | Kavitha,  Jaspreet,  Amrit | 28-june-2020 |
| Team Charter | 3 | 10-june-2020 | 13-june-2020 | Kavitha | 10-July- 2020 |
| Project charter | 3 | 11-june-2020 | 14-june-2020 | Jaspreet | 10-July- 2020 |
| **Analysis** | Use Cases | 3 | 15-june-2020 | 18-june-2020 | Jaspreet | 10-July- 2020 |
| System Sequence Diagram | 3 | 19-june-2020 | 21-june-2020 | Amrit | 10-July- 2020 |
| Class diagram | 3 | 20-june-2020 | 23-june-2020 | Kavitha | 10-July- 2020 |
| Interface Mock-up | 8 | 14-june-2020 | 1-july-2020 | Kavitha,  Jaspreet,  Amrit | 10-July- 2020 |
| **Design** | Database design | 3 | 1- July -2020 | 4- July -2020 | Jaspreet | 15-July- 2020 |
| User interface | 12 | 3- July -2020 | 15- July -2020 | Amrit | 18-July- 2020 |
| **Construction** | Register User | 1 | 15- July -2020 | 15- July -2020 | Kavitha | 25-July- 2020 |
| Phone validation | 1 | 15- July -2020 | 16- July -2020 | Amrit | 25-July- 2020 |
| Profile Edit | 2 | 16- July -2020 | 17- July -2020 | Jaspreet | 25-July- 2020 |
| Password Management | 1 | 17- July -2020 | 18- July -2020 | Kavitha | 08-Aug-2020 |
| Search for a specific service (Location) | 2 | 18- July -2020 | 19- July -2020 | Amrit | 24-July- 2020 |
| View detailed page of Available options | 1 | 19- July -2020 | 20- July -2020 | Jaspreet | 08-Aug-2020 |
| Rate and Review | 2 | 20- July -2020 | 21- July -2020 | Kavitha | 08-Aug-2020 |
| Scan QR Code | 1 | 21- July -2020 | 22- July -2020 | Amrit | 08-Aug-2020 |
| Location | 1 | 22- July -2020 | 23- July -2020 | Kavitha | 13-Aug-2020 |
| Help pages | 1 | 23- July -2020 | 24- July -2020 | Amrit | 13-Aug-2020 |
| Queue management | 1 | 24- July -2020 | 25- July -2020 | Kavitha | 13-Aug-2020 |
| **Testing** | Perform Application Testing | 4 | 26- July -2020 | 30- July -2020 | Jaspreet | 13-Aug-2020 |
| Document issues Found | 3 | 1-August -2020 | 4- August -2020 | Jaspreet |  |
| Correct issues found | 2 | 5-August -2020 | 7- August -2020 | Kavitha, Amrit |  |
| **Deployment** |  | 3 | 8-August -2020 | 11-August -2020 | Kavitha,  Jaspreet,  Amrit |  |